## Sheet1
Project: FIT 3140 Assignment 2
Risk Name | Description of Risk | Probability | Impact | Risk Reduction Strategy | Contigency Plans | Risk Owner
Faulty PIR Sensor | PIR Sensor not working properly. It may capture the movement of the pedestrian falsely. This may leads to inaccurate motion detection. | M | H | Make sure to take care of the parts carefully and cautiously | Ask for a replacement from the lecturer or buy a new one from a hardware store | Team members
Problem Connecting to Sever | Unable to send the motion sensor's data to the firebase storage, getting data from the motion sensor and/or listen to commands from the client side. | L | H | Seek consultation or use tutorials as references | Start the assignment early and seek for consultation. | Team members
Behind schedule for the tasks | Some tasks might take longer to complete than others. | M | H | Practice time management and start working on the assignment as soon as possible. Apply agile development cycle. | Set deadlines for each task and have a group meeting frequently until all the tasks completed. | Team members
Beaglebone Compatibility | Difficulty connecting to the laptop because of the ports or USB compatibility | L | H | Read the manual or seek consultation. | Ask for a replacement from the lecturer. | Team members
LED Burnout | Leaving the LED light connecting to the port for a long time causing a burnout. | L | L | Don't leave the LED light connecting to the port for a very long time. | Ask for a replacement from the lecturer. | Team members
Communication between members | There can be misunderstandings and misinterpretations between team members which may lead to a delay in completing the assignment. | L | M | Compromise and make sure everyone's understanding is clear. | If the situation is worsening, go and report to the lecturer. | Team members
Cloud Outages | The cloud service might experience server-breaking bugs that may knock out the service. | L | H | Ensure that the service has built-in safety features and it does not have a history of outages. | Have backup and share the files with all the team members. | Team members
Malicious Activity | The facilities that cloud data housed in is shared. There may be a chance for a malicious file to be uploaded to the same server which may affect the data. | L | H | Choose a provider that treats your data with sancitity. | Consult the lecturer for an extension and borrow another laptop. | Team members
VPN Issues | Some countries do not meet all the privacy laws and the requirements when it comes to storing a data. | L | H | Check if Malaysia VPN meets the requirements and has good connection speed. | Seek consultation from the lecturer. | Team members
Malware Problem | Unknown computer viruses, trojan horse or spyware may harm the computer by deleting, altering or stealing data. | L | H | Practice Smart Online Behaviour | Remove malware with the right software | Team members
Legend:
L - Low
M - Medium
H - High